## Main Sheet
Dated: | 2018-05-07 |  |  |  | Quote Expiry
BOQ for 100 Yards House at DHA 7 Ext. Karachi |  |  |  |  | 2018-05-15 |  |  | Our Expense
S.No | Description | Sqft | Floors | Total Sqft |  |  |  | Bill 2
| Sqft Calculation 100x9 = 900 sqft x 3 floors | 833.3333 | 3 | 2500 |  |  |  |  | Cost | Payment Made | Sub total | Payment Made By | Monthly
Turnkey Project Rates With Material |  |  |  |  | Qualty of Material |  |  | Structural Labor Nazim | 300000 | 300000 |  | Mustafa
1 | Complete Grey Structure | 2500 | 3000 | 7500000 | Tiles | UAE, Malaysia, China |  | Steel 3/8 is 4 Ton | 495000 | 495000
2 | Electrical |  |  |  | Plumbing Piping | UPVC |  | Steel 1/2 is 1 ton including wires |  |  |  | Mustafa/Azeem
3 | Plumbing |  |  |  | Gas Piping | GI |  | Cement 110 bags | 66500 | 66500 |  | Azeem
4 | Paint |  |  |  | Electrical Wiring | Pak Cable |  | Zareen Khan soling and digging | 56600 | 56600 |  | Azeem
5 | Flooring |  |  |  | Bahtroom fittings | Master |  | Speed money |  |  |  | Shahab bhai | 700 | 700
6 | Waterproofing |  |  |  | Sanitary | Porta |  | Water tank (CP) |  |  |  | Azeem | 4500 | 4500
7 | Boundary wall |  |  |  | Lights | Philips/Osaka |  | Generator pump (CP) |  |  |  | Azeem | 1450 | 1450 |  |  |  | Earth work excavation in all types of soil excluding hard rock requiring blasting for columnfoundations, trenches, drains, plinth beams,underground sump, cable trenches manholes,brick-footing etc. including dressing of sides and ramming bottoms including dewatering subsoilwater or chemically contaminated water, shoring,strutting labour, tools and tackles etc. and backfilling with the excavated or good quality earth in trenches, plinths, foundations under floors etc. Wherever required in layers. | Termite proofing using good quality to all the earth surfaces exposed to underground soil, to all foundations, beams and columns as well as retaining walls surfaces upto ground level from external side | Providing & laying Cement Concrete in ratio 1:4:8 lean and Reinforced Cement concrete at any level & height with minimum 1200 PSI Cylindrical strenght at 28 days with good quality of form work, compacting using vibrators, curing and removal of formwork etc using Sulphate Resistant Cement including all required inserts and plugs to required profiles and shapes etc. | Providing & laying at any level & height completely sealed water proofing required around basement areas on RCC/concrete and/ or masonary vertical and horizontal surfaces using bitumen | Providing, fabricating and placing at any level & height steel grade 72 (ASTM A-615 yield stress 72.000 PSI in all RCC membersincluding fabricating to profiles, 20 SWG steel binding wires, steel chairs and spacers (wastages, re-rolling margins, cut pieces etc.
8 | Plaster | [6 empty] | 500 Blocks 5" | 13000 | 13000 |  | Azeem
9 | Termite Proofing | [6 empty] | 300 cement bags | 175500 | 175000
10 | Sanitary Fixtures | [6 empty] | Raft 8/18/2018 |  |  |  |  | 35200
11 | Chokhat installations | [6 empty] | Pipe and petrol |  |  |  | 2000 | 2000
[8 empty] | Water tanker |  |  |  | 4000 | 4000
Staircase & Tower Calculation | [7 empty] | Water tank |  |  |  | 2500 | 2500
Option | Description | Sqft/Steps | Rate | Total | [6 empty] | Sub total | Misc Monthly
1 | Only Roof Stair Tower Compulsory (This is additional work) | 144 | 3030 | 436320 | [6 empty] | 1106100 | 15150
2 | Stair case with steps and finishing material (this is already included in our turnkey cost) | 432 | 3000 | 1296000 |  |  |  | Bill 3
3 | Under ground water tank in gallon (Additional cost) | 3000 | 180 | 540000 |  |  |  | Water pump |  |  |  | 1000 | 1000
|  |  | Grand Total | 8476320 |  |  |  | Shamsher |  |  |  | 15500 | 15500
| Additional Billing of UG Tank | 1566 | 180 | 281880 |  |  |  | Steel for wall | 189000 | 189000 | [6 empty] | 23500
|  |  | Grand Total | 8758200 |  |  |  | deen borthers | 19500 | 19500 |  |  |  |  | sadiq | 24500
[8 empty] | labor for steel tie of walls | 42000 | 42000 | [6 empty] | 50000
Terms & Conditions | [7 empty] | shutterring | 40000 | 40000 |  |  |  |  | Sadiq | 50000
1 | Urbanist is not responsible for arranging any permissions | [6 empty] | Cement 50 bags | 58000 | 58000
2 | The bills will be cleared on Actual Sqft | [6 empty] | Pump motor and fiiting | 2830 | 2830
3 | Payment schedule to be followed | [6 empty] | Electric material for conduiting | 6560 | 6560
4 | The quantities mentioned above may change according to "As per actual" basis | [6 empty] | Water tanker |  |  |  |  | 12250
5 | The above mentioned prices may vary as per client's material selection | [6 empty] | Water pump generator with petrol |  |  |  |  | 4000
6 | Payment mode can be cheque or online | [6 empty] | 6" block 400 blocks | 12400 | 12400
7 | The cheque will be in name of M/S Urbanist | [6 empty] | 5" blocks 1000 | 25000 | 25000 |  | sadiq
8 | For online transaction Bank Al-Habib, Account #: 11090981007962018 | [6 empty] | Mix, Crush, Sand | 83000 | 83000 |  | sadiq
9 | Above mention price is exclusive of Taxes | [6 empty] | Steel for basement roof | 191406 | 191406 |  | sadiq | [5 empty] | DHA 100 yard house
10 | Timeline will be decided once complete design and drawings are shared | [6 empty] | Bitumen coating | 4200 | 4200 |  | sadiq |  |  | Company expense |  |  | 1620000
11 | Incase of any kind of interruption in work or any kind of hinderence in building limitation, the work timeline will exceed | [6 empty] | suction pipe | 600 | 600 |  |  |  |  | Generator water pump | 12500 |  | 1890000
12 | Fancy lights and wall lights are not included in this cost | [6 empty] | fish lace | 250 | 250 | [7 empty] | 8400000 |  | 3360000
13 | Client will be solely responsible for any kind of peanlties charged on site due to permission issues | [6 empty] | measure tape | 250 | 250 | [7 empty] | 6510000 |  | #REF!
14 | Our rates does not include AC, lights, wood, metal, O.H Water tank and glass work | [6 empty] | glove | 60 | 60 | Sub total | Misc Monthly | [5 empty] | 1350000 | 3240000
15 | Electricity and water will be supplied by owner at site | [9 empty] | 675056 | 32750 | [5 empty] | 5160000
16 | Rates will be revised after expiry date | [15 empty] | material | 1800000
17 | The security is client's responsibility
18 | Cantilever making will be charged on as per actual basis
19 | Additional PKR. 3030/- per sqft will be charged for the stair tower along with steps | [18 empty] | 360000
20 | Under ground water tank 180/- per gallon
Payment Schedule | [18 empty] | civil | 945000
S.no | Description | Percentage % | Amount | Days | Received | received extra in 1st bill | Expenses | [11 empty] | electric | 250000
1 | Mobility Allowance | 10% | 847632 |  | 1000000 | 152368 | 1106100 | [11 empty] | plumbing | 250000
2 | On completion of foundation | 14% | 1186684.8 | 30 | 1034316.8 |  | 675056 | [11 empty] | painting | 250000
3 | On completion of Basement Roof | 10% | 847632 | 25 | 847632 | [14 empty] | 1695000
4 | On completion of 1st roof | 9% | 762868.8 | 25 | 762868.8 | [13 empty] | Steel | 1300000
5 | Completion of block masonary | 5% | 423816 | 45 | [14 empty] | cement | 400000
6 | On Completion of 2nd roof | 5% | 423816 | 25 |  | 254450 | [12 empty] | sand crush bond rohri boring | 400000
7 | On completion of internal plaster | 10% | 847632 | 30 | [14 empty] | Other mateial | 3500000
8 | On completion of plumbing | 4% | 339052.8 | 15 | [15 empty] | 7295000
9 | On completion of flooring | 5% | 423816 | 20 |  | 395063 |  |  | MT | 2500000
10 | On completion of paint | 8% | 678105.6 | 45 |  | -28753 |  |  | LMKT | 1200000
11 | On completion of stair tower | 5% | 423816 | 30 |  |  |  |  | Annexe | 975000
12 | On completion of under ground water tank | 6% | 790459.2 | 12 | 821880 |  |  |  | Dolmen | 1050000
13 | On completion of boundary wall | 4% | 339052.8 | 10 |  |  |  |  | ABM | 400000
14 | On handing over | 5% | 423816 | [5 empty] | S33 | 765868.8
15 | Extra Raft Billing |  | 450000 | [6 empty] | 6890868.8
|  | 100% | 9208200 | 312 | 4466697.6 |  | 1781156 |  | Approx profit | 6500000
[6 empty] | Difference | 2685541.6 |  |  | 2166666.6667
[6 empty] | Profit % | 60.12%
Our Costing
10208200
3222870
6985330
|  | Per Sqft Rate For us | 2794.132 |  |  |  | 900
|  |  | 2722870 |  |  |  | 2700
|  |  | 907623.3333 |  |  |  | 3288
|  |  | 90762.3333 | Tiling | 558960 |  |  |  | Total | 24229560.2667 | 1781156
|  |  | 3222870 | Bathroom & plumbing OH Tank | 490000 |  | 168
|  |  | 1074290 | Paint | 400000 |  | 672
|  |  | 107429 | Civil | 1700000 |  | 84 | Per Bathroom | Total | Outer Plumbing
|  |  |  | Steel | 1500000 |  | 588 | 72000 | 288000 | 488000
|  |  |  | Electric | 850000
|  |  |  | Cement | 400000
|  |  |  | W. Proofing | 200000 |  |  |  | 910000
|  |  |  | Termite | 40000
6138960
2455.584

## Bill 2-3
Date | 2018-08-27 | Bill # | 02/27Aug/18
Bill of Abbasi Residence as per Schedule | [5 empty] | unit
S.No | Description | Unit | Cost | Total | 3 tanker | 9500 | 3166.6667
1 | Payment of stage 2 at completion of foundation | 1 | 1186684.8 | 1186684.8 | Generator | 2500
2 | Received mobility advance |  | 1000000
| Actual amount to receive |  | 847632
| Balance |  | Less Balance | 152368
|  |  | Grand Total | 1034316.8
Date | 2018-08-27 | Bill # | 03/27Aug/18
Miscellaneous Expenses
S.No | Description | Unit | Cost | Total
1 | Water tankers | 3 | 3166.6667 | 9500
2 | Generator with petrol for 2 days | 2 | 1250 | 2500
3 | Paid to Shamsher chowkidar | 1 | 5000 | 5000
4 | Paid to Manzoor chowkidar | 1 | 1000 | 1000
|  |  | Total | 18000
|  |  | Grand Total | 1052316.8

## Bill 4-5
Date | 2018-10-03 | Bill # | 04/03Oct/18
Bill of Abbasi Residence as per Schedule
S.No | Description | Unit | Cost | Total
1 | Payment of stage 3 at completion of basement roof | 1 | 847632 | 847632
|  |  | Total | 847632
Date | 2018-10-03 | Bill # | 05/03Oct/18
Miscellaneous Expenses
S.No | Description | Unit | Cost | Total
1 | Water tankers | 4 | 3062.5 | 12250
2 | Water pump for curing with petrol | 20 | 250 | 5000
|  |  | Total | 17250
|  |  | Grand Total | 864882

## bill 6-7
Date | 2018-10-19 | Bill # | 06/19Oct/18
Bill of Abbasi Residence as per Schedule
S.No | Description | Unit | Cost | Total
1 | Payment of stage 4 at completion of 1st Roof | 1 | 762868.8 | 762868.8
2 | Under ground water tank completion in Gallon | 4566 | 180 | 821880
|  |  | Total | 1584748.8
Date | 2018-10-19 | Bill # | 07/19Oct/18
Miscellaneous Expenses
S.No | Description | Unit | Cost | Total
1 | Water tankers | 4 | 5000 | 20000
2 | Water pump for curing with petrol | 20 | 250 | 5000
3 | Guard Salary for month of sep 18 | 1 | 15500 | 15500
|  |  | Total | 40500
Account # | 1109-0981-007962-01-8
NTN # | 3117578-3 |  | Grand Total | 1625248.8
Cheque in Name of | M/S Urbanist

## Bill 8-9
Date | 2018-11-14 | Bill # | 08/14Nov/18
Bill of Abbasi Residence as per Schedule
S.No | Description | Unit | Cost | Total
1 | Payment of stage 6 at completion of 2nd Roof | 1 | 423816 | 423816
2 | Payment of Stage 5 at completion of block masonary | 1 | 423816 | 423816
|  |  | Total | 847632
Date | 2018-11-14 | Bill # | 09/14Nov/18
Miscellaneous Expenses
S.No | Description | Unit | Cost | Total
1 | Water tankers | 2 | 5000 | 10000
2 | Water pump for curing with petrol | 20 | 250 | 5000
0
|  |  | Total | 15000
Account # | 1109-0981-007962-01-8
NTN # | 3117578-3 |  | Grand Total | 862632
Cheque in Name of | M/S Urbanist

## Bill 10-11
Date | 2018-12-27 | Bill # | 10/27Dec/18
Bill of Abbasi Residence as per Schedule
S.No | Description | Unit | Cost | Total
1 | Payment of stage 11 at completion of star tower | 1 | 423816 | 423816
2 | Payment of Stage 15 at completion of Raft | 1 | 450000 | 450000
|  |  | Total | 873816
Date | 2018-12-27 | Bill # | 11/27Dec/18
Miscellaneous Expenses
S.No | Description | Unit | Cost | Total
1 | Water tankers | 2 | 5000 | 10000
2 | Generator and waterpump with petrol | 20 | 350 | 7000
3 | Guard Salary for month of Nov | 1 | 22000 | 22000
|  |  | Total | 39000
Account # | 1109-0981-007962-01-8
NTN # | 3117578-3 |  | Grand Total | 912816
Cheque in Name of | M/S Urbanist

## Bill 12
Date | 2019-01-29 | Bill # | 12/29Jan/19
Bill of Abbasi Residence for Plumbing, Electrical and Additional Bathroom Tanks
S.No | Description | Unit | Cost | Total
1 | Payment for Additional bathroom concealed tanks | 4 | 19500 | 78000
2 | 50% payment of stage 8 plumbing and electrical as per schedule | 1 | 169526.4 | 169526.4
|  |  | Total | 247526.4
Account # | 1109-0981-007962-01-8
NTN # | 3117578-3 |  | Grand Total | 329026.4
Cheque in Name of | M/S Urbanist

## Bill 13
Date | 2019-01-29 | Bill # | 13/25Jan/19
Miscellaneous Expenses
S.No | Description | Unit | Cost | Total
1 | Water tankers for nov | 2 | 5000 | 10000
2 | Water tankers for dec | 3 | 4500 | 13500
3 | Generator with petrol for Nov & Dec | 40 | 350 | 14000
4 | Guard Salary for month of Nov & Dec | 2 | 22000 | 44000
|  |  | Total | 81500
Account # | 1109-0981-007962-01-8
NTN # | 3117578-3
Cheque in Name of | M/S Urbanist

## Bill 14
Date | 2019-01-29 | Bill # | 14/29Jan/19
Bill of Abbasi Residence as per Schedule
S.No | Description | Unit | Cost | Total
1 | Payment of stage 7 internal plaster | 1 | 847632 | 847632
|  |  | Total | 847632
Account # | 1109-0981-007962-01-8
NTN # | 3117578-3 |  | Grand Total | 847632
Cheque in Name of | M/S Urbanist

## Bill 15
Date | 2019-03-05 | Bill # | 15/5Mar/19
Invoice for Additional Items Abbasi Residence
S.No | Description | Unit | Cost | Total
1 | Payment for Insulation Tiles | 780 | 150 | 117000
2 | Installation of Insulation Tiles with labor | 780 | 90 | 70200
3 | Cabling for security system | 1 | 80000 | 80000
|  |  | Total | 267200
Account # | 1109-0981-007962-01-8
NTN # | 3117578-3
Cheque in Name of | M/S Urbanist

## Bill 16
Date | 2019-03-05 | Bill # | 16/5Mar/19
Miscellaneous Expenses
S.No | Description | Unit | Cost | Total
1 | Water tankers for Jan | 3 | 5000 | 15000
2 | Water tankers for Feb | 3 | 5000 | 15000
3 | Generator with petrol for Jan & Feb | 40 | 500 | 20000
4 | Guard Salary for month of Jan & Feb | 2 | 22000 | 44000
|  |  | Total | 94000
Account # | 1109-0981-007962-01-8
NTN # | 3117578-3
Cheque in Name of | M/S Urbanist

## Bill 17
Date | 2019-03-27 | Bill # | 17/27Mar/19
Miscellaneous Expenses
S.No | Description | Unit | Cost | Total
1 | Payment of stage 13 completion of boundary wall | 1 | 339052.8 | 339052.8
|  |  | Total | 339052.8
Account # | 1109-0981-007962-01-8
NTN # | 3117578-3
Cheque in Name of | M/S Urbanist

## Bill 18
Date | 2019-04-10 | Bill # | 18/10Apr/19
Miscellaneous Expenses for additional work
S.No | Description | Sqft | Cost | Total
1 | Niche | 3 | 2000 | 6000
2 | Shower tray | 4 | 3000 | 12000
3 | Labor for steps excluding marble | 54 | 1000 | 54000
|  |  | Total | 72000
Account # | 1109-0981-007962-01-8
NTN # | 3117578-3
Cheque in Name of | M/S Urbanist

## Bill 19
Date | 3/27/201910apr | Bill # | 19/10Apr/19
Installation Material of Tiles Flooring for Abbasi Residence
S.No | Description | Sqft/Mtr | Cost | Total
1 | Material for Basement Tiling (sand,cement,bond) | 616.63 | 65 | 40080.95
2 | Material for Ground Floor Tiling | 807.587 | 65 | 52493.155 |  | 325.8845
3 | Material for First Floor Tiling | 1143.97 | 65 | 74358.05 |  | 122.9913 |  | 4.6555
4 | Material for Stairs Tiling | 94.5 | 65 | 6142.5 |  | 135.0093
5 | Material for Skirting | 461 | 65 | 29965 |  | 139.6648
0
537
|  |  | Total | 203039.655
Account # | 1109-0981-007962-01-8 |  |  |  |  | 94.5
NTN # | 3117578-3
Cheque in Name of | M/S Urbanist |  |  |  | 3050
3500
[5 empty] | 87.14% |  |  |  | 350
3150
1074
698.1
801.9
74.6648
[6 empty] | 139.6648 | 3500 | 6.0521 |  | 325.8845
[7 empty] | 488826.8156 | 21182.4953 |  | 16294.2272 | 102.4209
37.2439
130353.8175
358472.9981

## Bill 20
Date | 2019-04-10 | Bill # | 20/10Apr/19
Miscellaneous Expenses
S.No | Description | Unit | Cost | Total
1 | Water tankers for Mar | 3 | 5000 | 15000
2 | Generator with petrol for Mar | 22 | 500 | 11000
3 | Guard Salary for month of Jan & Feb | 2 | 22000 | 44000
4 | Plastic and plaster of paris to protect the tiles | 1 | 6500 | 6500
5 | Labor to lay plastic and plaster of paris | 1 | 6000 | 6000
6 | Labor for making roof gola skirting | 1 | 10000 | 10000
|  |  | Total | 92500
Account # | 1109-0981-007962-01-8
NTN # | 3117578-3
Cheque in Name of | M/S Urbanist

## Bill 21
Date | 2019-04-10 | Bill # | 21/10Apr/19
Overall Project Variance Bill for Abbasi Residence
S.No | Description | Unit | Cost | Total
1 | Difference in cement rate due to Increase in $ | 1000 | 100 | 100000
2 | Difference in steel rate due to increase in $ | 8 | 8000 | 64000
3 | Difference in Paint material rate due to increase in $ | 20 | 1500 | 30000
4
5
6
|  |  | Total | 194000
Account # | 1109-0981-007962-01-8
NTN # | 3117578-3
Cheque in Name of | M/S Urbanist

## Tiling Calculation
S.No | Floor | Tile Qty in Sqft | in Mtr | Rate as per BOQ | Total | Installation Material in Sqft/Rft | Cost in Sqft/Rft | Total
1 | Basement | 617 | 57.342 | 1400 | 80278.8104 | 617 | 30 | 18510
2 | Ground Floor | 808 | 75.0929 | 1400 | 105130.1115 | 808 | 30 | 24240
3 | First Floor | 1144 | 106.3197 | 1400 | 148847.5836 | 1144 | 30 | 34320
4 | Step Risers | 95 | 8.829 | 1400 | 12360.5948 | 95 | 30 | 2850
5 | Skirting | 167.31 | 15.5493 | 1400 | 21768.9591 | 167.31 | 30 | 5019.3
| Sub Total | 2831.31 | 263.1329 | 1400 | 368386.0595 | 2831.31 | 30 | 84939.3
6 | Add Wastage 15% | 424.6965 | 39.4699
7 | Total | 3256.0065 | 302.6028 | 1400 | 423643.9684 | Amount to be Paid
[6 empty] | Material Cost | Grand Total | 84939.3